## Overview
Role | Product Owner | Nguyen Van Hoang
| Scrum Master | Phan Minh Khoi
| Development Team | Nguyen Quang Gia Khoi Nguyen Xuan Truong Nguyen Dinh Manh
Scrum Event | Sprint Planning
Daily Meeting/Weekly Meeting
Sprint Review
Sprint Retrospective
Product Backlog/Sprint Backlog | List Stories
Sprint | Mục tiêu | Nội dung cần làm
Sprint 0 | Establish the project baseline and prepare the team and technical environment for development.
Sprint 1 | Deliver the initial application foundation that allows learners to securely access the platform and manage their basic learning profile.
Sprint 2 | Enable learners to browse predefined scenarios and complete a basic AI conversation session using the selected scenario and AI persona.
Sprint 3 | Enable learners to conduct a complete speech-based Japanese conversation with AI.
Sprint 4 | Evaluate learner conversation performance and provide meaningful feedback based on the completed conversation.
Sprint 5 | Provide learners with personalized learning materials and review activities based on their learning performance and identified weaknesses.
Sprint 6 | Enable learners to review their learning history and monitor their progress over time.
Sprint 7 | Integrate the major learning workflows, validate the complete system, and refine the product based on testing and feedback.

## Danh sách UC để đối chiếu
No | Code | Feature | Use Cases | Complexity | Priority | Sprint | Usecase | Note
1 | UC-01 | FE-01 | Register Account | Low | High | Sprint 1
2 | UC-02 | FE-01 | Log In | Low | High | Sprint 1 | UC13
3 | UC-03 | FE-01 | Log In with Google | Low | High | Sprint 1 | UC10
4 | UC-04 | FE-01 | Log Out | Low | High | Sprint 1 | UC11
5 | UC-05 | FE-01 | Reset Password | Medium | High | Sprint 1 | UC12
6 | UC-06 | FE-01 | Change Password | Low | High | Sprint 1 | UC15
7 | UC-07 | FE-01 | View Learner Profile | Low | High | Sprint 1 | UC16
8 | UC-08 | FE-01 | Update Learner Profile | Low | High | Sprint 1 | UC17
9 | UC-09 | FE-01 | Feedback and Report an Issue | Medium | Medium
10 | UC-10 | FE-02 | View Credit Packages | Low | High | Sprint 1 | UC19
11 | UC-11 | FE-02 | Purchase Credits | Medium | High | Sprint 1 | UC20
12 | UC-12 | FE-02 | View Credit History | Low | Medium | Sprint 1
13 | UC-13 | FE-02 | Add Credit Package | Medium | High | Sprint 1 | UC-4
14 | UC-14 | FE-02 | Edit Credit Package | Low | High | Sprint 1
15 | UC-15 | FE-02 | Delete Credit Package | Low | High | Sprint 1 | UC-6,7
16 | UC-16 | FE-03 | View Scenarios List (Learner/Admin) | Low | High | Sprint 2 | UC14
17 | UC-17 | FE-03 | Search a Scenario | Low | Medium | Sprint 2
18 | UC-18 | FE-03 | View Scenario Details | Low | High | Sprint 2 | UC21,22,23,24
19 | UC-19 | FE-03 | Practice AI Scenario Conversation | High | High | Sprint 2 | UC25
20 | UC-20 | FE-03 | View Conversation Result History | Medium | Medium | Sprint 2 | UC26,27
21 | UC-21 | FE-03 | View Conversation Result Detail | Medium | Medium | Sprint 2 | UC28
22 | UC-22 | FE-03 | Add Scenario | Medium | High | Sprint 2 | UC80,81,82
23 | UC-23 | FE-03 | Edit Scenario | Low | High | Sprint 2 | UC85
24 | UC-24 | FE-03 | Delete Scenario | Low | High | Sprint 2 | UC86,87,88
25 | UC-25 | FE-04 | View Shadowing Contents List | Low | High | Sprint 2 | UC29
26 | UC-26 | FE-04 | Search a Shadowing Content | Low | Medium | Sprint 2
27 | UC-27 | FE-04 | Practice Shadowing | High | High | Sprint 2 | UC30
28 | UC-28 | FE-04 | View Shadowing Assessment History | Medium | Medium | Sprint 2
29 | UC-29 | FE-04 | Add Shadowing Content | Medium | High | Sprint 2 | UC91,92,93
30 | UC-30 | FE-04 | Edit Shadowing Content | Low | High | Sprint 2
31 | UC-31 | FE-04 | Delete Shadowing Content | Low | High | Sprint 2
32 | UC-32 | FE-05 | Study Daily Recommended Flashcards | Not measured | Medium |  | UC31
33 | UC-33 | FE-05 | View Vocabulary Group List | Low | High |  | UC32
34 | UC-34 | FE-05 | View Vocabulary Group Details | Low | High |  | UC34,35
35 | UC-35 | FE-05 | Search a Vocabulary | Low | Medium |  | UC36
36 | UC-36 | FE-05 | Study a Vocabulary | Medium | High |  | UC37
37 | UC-37 | FE-05 | Review Vocabulary through Flashcards | Medium | Medium |  | UC38
38 | UC-38 | FE-05 | View Grammar Group List | Low | High |  | UC39,40,41,42,43,44
39 | UC-39 | FE-05 | View Grammar Group | Low | High |  | UC45,46,47
40 | UC-40 | FE-05 | Search a Grammar | Low | Medium |  | UC48,49
41 | UC-41 | FE-05 | Study Grammar | Medium | High |  | UC66-70
42 | UC-42 | FE-05 | Review Grammar through Flashcards | Medium | Medium |  | UC50,51,52,53,54
43 | UC-43 | FE-05 | Bookmark Learning Contents | Low | Medium |  | UC61-65
44 | UC-44 | FE-05 | View Bookmarked Learning Contents | Low | Medium |  | UC71-79
45 | UC-45 | FE-05 | Add Vocabulary to Group | Medium | High
46 | UC-46 | FE-05 | Assign an existing Vocabulary to Group | Low | Medium
47 | UC-47 | FE-05 | Edit Vocabulary | Low | High
48 | UC-48 | FE-05 | Remove Vocabulary from Group | Low | High
49 | UC-49 | FE-05 | Add Grammar to Group | Medium | High |  | UC-1
50 | UC-50 | FE-05 | Assign an existing Grammar to Group | Low | Medium |  | UC-3
51 | UC-51 | FE-05 | Edit Grammar | Low | High |  | UC-2
52 | UC-52 | FE-05 | Remove Grammar from Group | Low | High |  | UC-5
53 | UC-53 | FE-06 | Search & Filter Users | Low | Medium |  | UC66-70
54 | UC-54 | FE-06 | Change User Account Status (Ban/Unban) | Low | Medium |  | UC55-60
55 | UC-55 | FE-06 | View Learner Feedback | Medium | Medium |  | UC-8

## Product Backlog
No | Code | User Story | Priority | Sprint | Usecase | Note
1 | U001 | As a Guest, I want to register an account using my email or Google, so that I can start accessing the platform. | High
2 | U002 | As a Learner, I want to log in securely with my accounts, so that I can access my saved learning progress. | High |  | UC13
3 | U003 | As a User, I want to log out of my account, so that my account stays secure when I finish using the device. | High |  | UC10
4 | U004 | As a User, I want to reset my forgotten password via email, so that I can regain access if I forget my login details. | High |  | UC11
5 | U005 | As a User, I want to change my password within account settings, so that I can proactively protect my account security. | High |  | UC12
6 | U006 | As a Learner, I want to view and edit my personal profile, so that my display information is always up to date. | Medium |  | UC15
7 | U007 | As a Learner, I want to select my Japanese level and daily study goal, so that the app suggests fitting lessons. | High |  | UC16
8 | U008 | As a Learner, I want to review a few flashcards daily, so that I have vocabulary and grammar ready before speaking. | Medium |  | UC17
9 | U009 | As a Learner, I want to jump straight into a conversation scenario after flashcards, so that I can train new conversation everyday. | Medium |  | UC18
10 | U010 | As a Learner, I want to receive specific scenario details before chatting with AI, so that I know clearly what to achieve. | High |  | UC19
11 | U011 | As a Learner, I want to chat and speak with AI in real-world scenarios, so that I can build fast speaking reflexes. | High |  | UC20
12 | U012 | As a Learner, I want to see color feedback on my voice, so that I know exactly which words I mispronounced. | Medium
13 | U013 | As a Learner, I want to click once on bold grammar to see a quick pop-up, so that I can understand the meaning immediately. | Medium |  | UC14
14 | U014 | As a Learner, I want to double-click on grammar to open its full detail page, so that I can study more examples in depth. | Medium |  | UC21,22,23,24
15 | U015 | As a Learner, I want to get clear feedback on grammar, vocabulary, and keigo after each chat, so that I can correct my mistakes. | High |  | UC25
16 | U016 | As a Learner, I want to review my past practice history and score improvements, so that I can see my progress over time. | Low |  | UC26,27
17 | U017 | As a Learner, I want to get daily reviews based on my past errors, so that I can fix my weak points consistently. | High |  | UC28
18 | U018 | As a Learner, I want to get hint suggestions during an AI conversation, so that I can continue the dialogue when I get stuck on words. | Low |  | UC29
19 | U019 | As a Learner, I want to replay my recorded voice alongside the sample audio, so that I can clearly hear the difference in my intonation. | Low |  | UC30
20 | U020 | As a Learner, I want to bookmark useful words and dialogue lines during practice, so that I can review them anytime in my personal notebook. | Medium
21 | U021 | As a Learner, I want to set a customized daily reminder notification, so that I never forget study time. | Medium |  | UC31
22 | U022 | As a Learner, I want to view a weekly skill progress report, so that I can clearly see the improvement trend across my core speaking skills. | High |  | UC32
23 | U023 | As a Learner, I want to track my daily study streak, so that I stay motivated to practice Japanese every day. | Low |  | UC34,35
24 | U024 | As a Learner, I want to receive rewards and badges when hitting streak milestones, so that I feel recognized for my consistency. | Low |  | UC36
25 | U025 | As a Learner, I want the system to check my skill scores to decide if I can level up JLPT tier, so that I only advance when my skills are truly ready. | Medium |  | UC37
26 | U026 | As an Admin, I want to search, filter, and sort the user list, so that I can easily look up any learner in the system. | High |  | UC38
27 | U027 | As an Admin, I want to ban or unban a user account with a reason, so that I can handle policy violations and maintain system safety. | High |  | UC39,40,41,42,43,44
28 | U028 | As an Admin, I want to create, update, and publish conversation scenarios, so that learners have up-to-date conversation practice content. | High |  | UC45,46,47
29 | U029 | As an Admin, I want to manage categories and JLPT difficulty levels, so that learning content is structured systematically. | High |  | UC48,49
30 | U030 | As an Admin, I want to view users' learning history, so that I can track their study progress and activities. | Medium |  | UC66-70
31 | U031 | As an Admin, I want to view system analytics, so that I can measure overall platform engagement. | Medium |  | UC50,51,52,53,54 | active users, average study time, streak retention
32 | U032 |  |  |  | UC61-65
33 | U033 |  |  |  | UC71-79
34 | U034 |  |  |  | UC66-70
35 | U035 |  |  |  | UC55-60
36 | U036 |  |  |  | UC80,81,82
37 | U037 |  |  |  | UC85
38 | U038 |  |  |  | UC86,87,88
39 | - | Init codebase BE and CI/CD | High | Sprint 1
40 | - | Init codebase FE and CI/CD | High | Sprint 1
41 | - | Config DB for project | High | Sprint 1
42 | - | Prepare Product Backlog | High | Sprint 1
43 | U040 |  |  |  | UC-1
44 | U041 |  |  |  | UC-3
45 | U042 |  |  |  | UC-2
46 | U043 |  |  |  | UC-5
47 | U044 |  |  |  | UC-4
48 | U045
49 | U046 |  |  |  | UC-6,7
50 | U047 |  |  |  | UC-8
51 | U048 |  |  |  | UC91,92,93
54 | U051
55 | U052
56 | U053
57 | U054
58 | U055
59 | U056
60 | U057
61 | U058
62 | U059
63 | U060
64 | U061
65 | U062
66 | U062

## Sprint 1
Start Date | 2026-08-31
End Date | 2026-09-13
STT | Code | Column 10 | Use case | Priority | Status | PIC | Start Date | End Date | Issue
1 |  |  | Init codebase BE and CI/CD | High | Done | Hoàng |  |  | No
2 |  |  | Init codebase FE and CI/CD | High | Done | Minh Khôi |  |  | No
3 |  |  | Config DB for project | High | Done | Hoàng |  |  | No
4 |  |  | Prepare Product Backlog | High | Done | Hoàng |  |  | No
5 | UC-01 | FE-01 | Register Account | High | Done | Hoàng | 2026-09-14
6 | UC-02 | FE-01 | Log In | High | Done | Hoàng | 2026-09-14
7 | UC-03 | FE-01 | Log In with Google | Medium | Done | Hoàng | 2026-09-14
8 | UC-04 | FE-01 | Log Out | High | Done | Hoàng | 2026-09-14
9 | UC-05 | FE-01 | Reset Password | High | In Review | Trường | 2026-09-14
10 | UC-06 | FE-01 | Change Password | High | In Review | Trường | 2026-09-14
11 | UC-07 | FE-01 | View Learner Profile | High | Done | Minh Khôi | 2026-09-14
12 | UC-08 | FE-01 | Update Learner Profile | High | Done | Minh Khôi | 2026-09-14
13 | UC-11 | FE-02 | View Credit Packages | High | In Review | Gia Khôi | 2026-09-14
14 | UC-12 | FE-02 | Purchase Credits | High | In Review | Mạnh | 2026-09-14
15 | UC-13 | FE-02 | View Credit History | Medium | In Review | Mạnh | 2026-09-14
16 | UC-14 | FE-02 | Add Credit Package | High | In Review | Gia Khôi | 2026-09-14
17 | UC-15 | FE-02 | Edit Credit Package | High | In Review | Gia Khôi | 2026-09-14
18 | UC-16 | FE-02 | Delete Credit Package | High | In Review | Gia Khôi | 2026-09-14

## Sprint 2
Start Date | 2026-09-14
End Date | 2026-09-27
STT | Code | Column 10 | Use case | Priority | Status | PIC | Start Date | End Date | Issue
1 |  |  | Init codebase BE and CI/CD | High | Done | Hoàng |  |  | No
2 |  |  | Init codebase FE and CI/CD | High | Done | Minh Khôi |  |  | No
3 |  |  | Config DB for project | High | Done | Hoàng |  |  | No
4 |  |  | Prepare Product Backlog | High | Done | Hoàng |  |  | No
5 | UC-01 | FE-01 | Register Account | High | In Progress | Hoàng | 2026-09-14
6 | UC-02 | FE-01 | Log In | High | In Progress | Hoàng | 2026-09-14
7 | UC-03 | FE-01 | Log In with Google | Medium | In Progress | Hoàng | 2026-09-14
8 | UC-04 | FE-01 | Log Out | High | In Progress | Hoàng | 2026-09-14
9 | UC-05 | FE-01 | Reset Password | High | In Progress | Trường | 2026-09-14
10 | UC-06 | FE-01 | Change Password | High | In Progress | Trường | 2026-09-14
11 | UC-07 | FE-01 | View Learner Profile | High | In Progress | Minh Khôi | 2026-09-14
12 | UC-08 | FE-01 | Update Learner Profile | High | In Progress | Minh Khôi | 2026-09-14
13 | UC-11 | FE-02 | View Credit Packages | High | In Progress | Gia Khôi | 2026-09-14
14 | UC-12 | FE-02 | Purchase Credits | High | In Progress | Mạnh | 2026-09-14
15 | UC-13 | FE-02 | View Credit History | Medium | In Progress | Mạnh | 2026-09-14
16 | UC-14 | FE-02 | Add Credit Package | High | In Progress | Gia Khôi | 2026-09-14
17 | UC-15 | FE-02 | Edit Credit Package | High | In Progress | Gia Khôi | 2026-09-14
18 | UC-16 | FE-02 | Delete Credit Package | High | In Progress | Gia Khôi | 2026-09-14

## Sheet9 (hidden)
Start Date
End Date
STT | Code | User Story | Priority | Status | PIC | Start Date | End Date | Issue
1 | U001 | As a Tourist, I want to view general information about Ngũ Hành Sơn (homepage), so that I can understand the history and visiting rules. | High | To-do | N/A
2 | U002 | As a Tourist, I want to view a list of Destinations with basic info, so that I can browse available places to visit. | High | To-do | N/A
3 | U003 | As a Tourist, I want to view details of a specific Destination, so that I can learn more about it before visiting. | High | To-do | N/A
4 | U006 | As a Tourist, I want to view a list of Official Events, so that I can know what festivals are happening. | Medium | To-do | N/A
5 | U007 | As a Tourist, I want to view details of an Event, so that I can plan my time to participate. | Medium | To-do | N/A
6 | U008 | As a Tourist, I want to view a list of Blogs/News, so that I can read updates about the site. | Low | To-do | N/A
7 | U009 | As a Tourist, I want to read Blog details, so that I can get full information on a topic. | Low | To-do | N/A
8 | U031 | As an Admin, I want to manage Destinations (Create, Update, Hide, List), so that the app content is up to date. | High | To-do | N/A
9 | U032 | As an Admin, I want to manage Official Events (Create, Update, Cancel, List), so that visitors know about activities. | Medium | To-do | N/A
10 | U033 | As an Admin, I want to manage Blogs and Categories (Create, Update, Delete, List), so that I can publish news. | Medium | To-do | N/A

## Sheet10 (hidden)
Start Date
End Date
STT | Code | User Story | Priority | Status | PIC | Start Date | End Date | Issue
1 | U006 | As a Tourist, I want to view a list of Official Events, so that I can know what festivals are happening. | Medium | To-do | N/A
2 | U007 | As a Tourist, I want to view details of an Event, so that I can plan my time to participate. | Medium | To-do | N/A
3 | U008 | As a Tourist, I want to view a list of Blogs/News, so that I can read updates about the site. | Low | To-do | N/A
4 | U009 | As a Tourist, I want to read Blog details, so that I can get full information on a topic. | Low | To-do | N/A
5 | U020 | As a Tourist, I want to view and update my Personal Profile, so that my account information is accurate. | Medium | To-do | N/A
6 | U032 | As an Admin, I want to manage Official Events (Create, Update, Cancel, List), so that visitors know about activities. | Medium | To-do | N/A
7 | U033 | As an Admin, I want to manage Blogs and Categories (Create, Update, Delete, List), so that I can publish news. | Medium | To-do | N/A

## Sheet11 (hidden)
Start Date
End Date
STT | Code | User Story | Priority | Status | PIC | Start Date | End Date | Issue
1 | U014 | As a Tourist, I want to manage my Shopping Cart (Add, View, Update, Remove), so that I can prepare to buy multiple tickets. | High | To-do | N/A
2 | U015 | As a Tourist, I want to apply a Voucher Code, so that I can get a discount on my order. | Medium | To-do | N/A
3 | U016 | As a Tourist, I want to Checkout and Process Online Payment (PayOS), so that I can complete my booking. | High | To-do | N/A
4 | U017 | As a Tourist, I want to view Transaction History, so that I can review my past purchases. | Medium | To-do | N/A
5 | U018 | As a Tourist, I want to view Transaction Details/Invoice, so that I can see exactly what I paid for. | Medium | To-do | N/A
6 | U019 | As a Tourist, I want to download my E-ticket (Receipt), so that I can use the QR code for entry. | High | To-do | N/A
7 | U035 | As an Admin, I want to manage Ticket Types and Dynamic Pricing, so that I can configure entrance fees. | High | To-do | N/A

## Sheet12 (hidden)
Start Date
End Date
STT | Code | User Story | Priority | Status | PIC | Start Date | End Date | Issue
1 | U010 | As a Tourist, I want to view a list of Workshops, so that I can find craft classes to join. | High | To-do | N/A
2 | U011 | As a Tourist, I want to view Workshop details (syllabus, price), so that I can decide to buy a ticket. | High | To-do | N/A
3 | U026 | As a Vendor, I want to update my Profile and view Dashboard, so that I can manage my business info and stats. | Medium | To-do | N/A
4 | U027 | As a Vendor, I want to manage Workshop Templates (Create, Update, Delete, List) and Register them, so that I can offer classes. | High | To-do | N/A
5 | U028 | As a Vendor, I want to manage Sessions (Create, View Calendar, Cancel), so that tourists can book specific times. | High | To-do | N/A
6 | U036 | As an Admin, I want to manage Vendors (List, Detail, Create Account), so that I can control partner access. | High | To-do | N/A
7 | U037 | As an Admin, I want to approve/reject Workshop Templates and view Workshop List, so that I ensure quality. | High | To-do | N/A

## Process
Process cho 1 sprint
1. Lập Kế Hoạch Sprint (Sprint Planning)
· Khi nào? Buổi sáng đầu tiên của mỗi Sprint (ví dụ: sáng thứ Hai, tuần 1, 3, 5, 7).
· Mục tiêu: Cả nhóm cùng nhau trả lời hai câu hỏi:
1. Chúng ta có thể làm gì trong Sprint này? -> Product Owner (một bạn trong nhóm) sẽ trình bày các User Story có ưu tiên cao nhất từ Product Backlog. Nhóm sẽ thảo luận và quyết định chọn một lượng công việc mà họ tin rằng có thể hoàn thành trong 2 tuần (dựa vào Velocity ước tính).
2. Chúng ta sẽ làm nó như thế nào? -> Nhóm sẽ chia nhỏ các User Story đã chọn thành các công việc kỹ thuật cụ thể (sub-tasks), ví dụ: "Tạo API", "Thiết kế component UI", "Viết test case",...
· Kết quả: Một Sprint Backlog (danh sách công việc cho sprint) và một Mục tiêu Sprint (Sprint Goal) rõ ràng.
2. Quá Trình Phát Triển (The Sprint Itself)
· Khi nào? Xuyên suốt 2 tuần của Sprint.
· Công việc: Đây là lúc các thành viên thực sự bắt tay vào làm việc.
o Lập trình: Viết code cho các chức năng đã chọn.
o Thiết kế "Just-in-time": Chỉ thiết kế chi tiết (UI, CSDL) cho những tính năng đang làm trong sprint hiện tại, không thiết kế trước cho toàn bộ hệ thống.
o Kiểm thử (Testing): Quan trọng: Testing được thực hiện song song với lập trình. Một tính năng được code xong thì phải được test ngay lập tức, không đợi đến cuối dự án.
o Review code: Các thành viên xem và góp ý code của nhau để đảm bảo chất lượng.
· Sự kiện quan trọng hàng ngày: Họp Hàng Ngày (Daily Scrum)
o Thời gian: 15 phút cố định mỗi sáng.
o Mục đích: Cả nhóm đứng thành vòng tròn và mỗi người trả lời 3 câu hỏi:
1. Hôm qua bạn đã làm gì?
2. Hôm nay bạn sẽ làm gì?
3. Bạn có gặp khó khăn/trở ngại nào không?
o Đây không phải là buổi báo cáo cho Scrum Master, mà là để cả nhóm đồng bộ thông tin và hỗ trợ lẫn nhau.
3. Sơ Kết Sprint (Sprint Review)
· Khi nào? Buổi chiều cuối cùng của Sprint (ví dụ: chiều thứ Sáu, tuần 2, 4, 6, 8).
· Mục tiêu: Trình diễn sản phẩm và nhận phản hồi.
· Hoạt động: Nhóm sẽ DEMO trực tiếp sản phẩm đang chạy (những gì đã hoàn thành trong Sprint) cho các bên liên quan (có thể là giảng viên, hoặc các thành viên khác trong nhóm đóng vai khách hàng).
· Lưu ý: Đây là buổi demo về sản phẩm, không phải buổi trình bày slide về những gì đã làm. Feedback nhận được sẽ được đưa vào Product Backlog để xem xét cho các Sprint sau.
4. Cải Tiến Sprint (Sprint Retrospective)
· Khi nào? Ngay sau buổi Sprint Review, là hoạt động cuối cùng của Sprint.
· Mục tiêu: Nhìn lại quy trình làm việc của nhóm để tìm ra cách cải thiện.
· Hoạt động: Cả nhóm (chỉ có team, không có khách hàng) cùng thảo luận 3 câu hỏi:
1. Trong 2 tuần qua, điều gì chúng ta đã làm tốt?
2. Điều gì chúng ta làm chưa tốt?
3. Chúng ta có thể làm gì để cải thiện trong Sprint tới?
· Đây là cơ hội để nhóm tự tối ưu hóa cách thức hợp tác và hiệu suất làm việc của chính mình.
Sau khi kết thúc bước 4, vòng lặp Sprint mới sẽ lại bắt đầu với bước 1.
Process chung cho toàn Project
Ví dụ thực hiện đề tài: Learning Management System (LMS)
Sprint 0: Chuẩn bị (Khoảng 2-3 ngày, không tính vào 4 sprint chính)
· Mục tiêu: Thiết lập nền tảng để nhóm có thể bắt đầu Sprint 1 một cách trơn tru.
· Công việc:
o Tổ chức buổi Kick-off, phân vai (có thể luân phiên vai trò Scrum Master, Product Owner).
o Thảo luận và chọn stack công nghệ (ReactJS, NodeJS, MySQL,...).
o Tạo repo Git/GitHub, thiết lập cấu trúc thư mục cơ bản.
o Thiết lập môi trường làm việc (cài đặt các công cụ cần thiết).
o Tạo Product Backlog ban đầu trên Trello/Jira với các User Story chính. Không cần phân tích quá sâu.
Kế Hoạch 4 Sprint
Sprint 1: Xây dựng chức năng xem và quản lý khóa học cơ bản
· Mục tiêu Sprint: Kết thúc Sprint, Admin có thể đăng nhập và tạo/xem/sửa/xóa khóa học. Sinh viên (chưa cần đăng nhập) có thể xem danh sách các khóa học trên trang chủ.
· Tại sao?: Đây là tính năng lõi. Không có khóa học thì hệ thống không có giá trị. Nó tạo ra một sản phẩm có thể demo được ngay lập tức.
· Các User Story cần làm:
o Là Admin, tôi muốn đăng nhập vào hệ thống để quản lý.
o Là Admin, tôi muốn tạo/sửa/xóa một khóa học.
o Là người dùng, tôi muốn xem danh sách các khóa học hiện có.
Sprint 2: Triển khai xác thực người dùng và chức năng đăng ký khóa học
· Mục tiêu Sprint: Sinh viên có thể đăng ký/đăng nhập và ghi danh vào một khóa học. Giảng viên có thể xem danh sách sinh viên trong khóa học của mình.
· Tại sao?: Mở rộng từ Sprint 1, cho phép tương tác đầu tiên của người dùng chính (sinh viên) với sản phẩm.
· Các User Story cần làm:
o Là sinh viên, tôi muốn đăng ký tài khoản.
o Là sinh viên, tôi muốn đăng nhập vào hệ thống.
o Là sinh viên, tôi muốn nhấn nút "Ghi danh" vào một khóa học.
o Là giảng viên, tôi muốn xem danh sách sinh viên đã ghi danh trong khóa học của tôi.
Sprint 3: Xây dựng nội dung và tương tác trong khóa học
· Mục tiêu Sprint: Giảng viên có thể thêm các bài học, tài liệu vào khóa học. Sinh viên đã ghi danh có thể xem các nội dung đó.
· Tại sao?: Làm cho khóa học trở nên "sống động" với nội dung thực tế.
· Các User Story cần làm:
o Là giảng viên, tôi muốn thêm các chương/bài học vào khóa học.
o Là giảng viên, tôi muốn tải lên tài liệu (PDF, DOCX) cho một bài học.
o Là sinh viên, tôi muốn xem danh sách bài học trong khóa học đã ghi danh.
o Là sinh viên, tôi muốn tải về tài liệu từ một bài học.
Sprint 4: Hoàn thiện tính năng nộp bài, chấm điểm và tối ưu
· Mục tiêu Sprint: Hoàn thiện luồng học tập cơ bản với chức năng bài tập và chấm điểm. Tối ưu giao diện và sửa các lỗi còn tồn đọng để chuẩn bị cho buổi demo cuối cùng.
· Tại sao?: Hoàn thành vòng lặp tương tác chính: Giảng viên ra bài -> Sinh viên nộp bài -> Giảng viên chấm điểm.
· Các User Story cần làm:
o Là giảng viên, tôi muốn tạo một bài tập và đặt hạn nộp.
o Là sinh viên, tôi muốn nộp bài tập (upload file).
o Là giảng viên, tôi muốn chấm điểm và nhận xét cho bài nộp của sinh viên.
o (Nhiệm vụ kỹ thuật) Cải thiện UI/UX trên các trang chính.
o (Nhiệm vụ kỹ thuật) Sửa các bug đã được báo cáo.

## Detail Plan
Ví dụ thực hiện đề tài: Learning Management System (LMS)
Sprint 1: Xây dựng chức năng xem và quản lý khóa học cơ bản (Ngày 14/10 - 24/10)
· Sprint Goal: Admin có thể đăng nhập, quản lý (CRUD) khóa học. Người dùng có thể xem danh sách khóa học.
· Các Sự Kiện Scrum:
o Sprint Planning (Ngày 14/10): Cả nhóm họp để chọn các User Story trên và chia thành các task nhỏ (sub-task).
o Daily Scrum (15 phút mỗi ngày): Họp nhanh để cập nhật tiến độ.
o Sprint Review (Ngày 24/10, buổi chiều): DEMO sản phẩm chạy được cho cả nhóm và "khách hàng".
o Sprint Retrospective (Ngày 24/10, cuối giờ): Nhìn lại quá trình làm việc để cải tiến cho Sprint 2.
Bảng công việc (Sprint Backlog) cho Sprint 1 trên Trello/Jira:
Công việc | Người phụ trách | Công việc cần làm (Sub-tasks) | Deadline | Kết quả/Deliverable
User Story 1: Login cho Admin | Thành viên A | - Thiết kế CSDL cho bảng users (chỉ cần username, password, role). - Viết API POST /login. - Tạo giao diện trang Login. - Tích hợp API và UI, xử lý token. | Ngày 5 (17/10) | Chức năng Login hoạt động.
User Story 2: CRUD Khóa học | Thành viên B, C | - Thiết kế CSDL cho bảng courses. - Viết API GET, POST, PUT, DELETE /courses. - Tạo giao diện trang quản lý khóa học (danh sách, form thêm/sửa). - Tích hợp API và UI. | Ngày 8 (22/10) | Trang Admin có thể thêm/sửa/xóa khóa học.
User Story 3: Hiển thị DS Khóa học | Thành viên D | - Tạo giao diện trang chủ. - Tạo component CourseCard để hiển thị thông tin từng khóa học. - Gọi API GET /courses và hiển thị dữ liệu ra trang chủ. | Ngày 9 (23/10) | Trang chủ hiển thị danh sách khóa học lấy từ DB.
Kiểm thử chéo & Sửa lỗi | Cả team | - Thành viên A test chức năng của B, C. - Thành viên D test chức năng của A. - Log bug và fix. | Ngày 10 (24/10) | Sản phẩm ổn định, sẵn sàng cho Sprint Review.
Sprint 2: Triển khai xác thực người dùng và chức năng đăng ký khóa học (ngày 27/10 -> 7/11)
Sprint Goal: Sinh viên có thể đăng ký/đăng nhập và ghi danh vào một khóa học. Giảng viên có thể xem danh sách sinh viên trong khóa học của mình.
Các sự kiện Scrum:
o Sprint Planning (Ngày 27/10): Cả nhóm họp để chọn các User Story trên và chia thành các task nhỏ (sub-task).
o Daily Scrum (15 phút mỗi ngày): Họp nhanh để cập nhật tiến độ.
o Sprint Review (Ngày 7/11, buổi chiều): DEMO sản phẩm chạy được cho cả nhóm và "khách hàng".
o Sprint Retrospective (Ngày 7/11, cuối giờ): Nhìn lại quá trình làm việc để cải tiến cho Sprint 3.
Bảng công việc (Sprint Backlog) cho Sprint 2 trên Trello/Jira:
Công việc | Người phụ trách | Công việc cần làm (Sub-tasks) | Deadline | Kết quả/Deliverable
User Story 1: Đăng ký tài khoản | Thành viên A | - Thiết kế CSDL bảng users (username, password, role) | (27/10) | Chức năng đăng ký hoạt động, lưu user vào DB
- Viết API POST /signup
- Tạo giao diện đăng ký
- Tích hợp API và UI
User Story 2: Đăng nhập hệ thống | Thành viên B | - Viết API POST /login | (31/10) | Đăng nhập thành công, sinh viên truy cập hệ thống
- Tạo giao diện đăng nhập
- Xử lý xác thực (JWT/session)
- Tích hợp API và UI
User Story 3: Ghi danh vào khóa học | Thành viên C | - Thêm field ghi danh vào bảng courses/users | (03/11) | Sinh viên ghi danh vào khóa học trên giao diện
- Viết API POST /enroll
- Tạo nút ghi danh trên UI
- Tích hợp API và UI
User Story 4: Xem danh sách sinh viên | Thành viên D | - Viết API GET /course/:id/students | (07/11) | Giảng viên xem danh sách sinh viên đã ghi danh
- Tạo giao diện danh sách sinh viên
- Hiển thị cho giảng viên
- Viết test case
Kiểm thử chéo & Sửa lỗi | Cả team | - Thành viên A test chức năng của B, C | (07/11) | Sản phẩm ổn định, sẵn sàng cho Sprint Review
- Thành viên D test chức năng của A
- Log bug và fix
Sprint 3: Xây dựng nội dung và tương tác trong khóa học (ngày 10/11 -> 21/11)
Sprint Goal: Giảng viên có thể thêm các bài học, tài liệu vào khóa học. Sinh viên đã ghi danh có thể xem các nội dung đó.
Các sự kiện Scrum:
o Sprint Planning (Ngày 10/11): Cả nhóm họp để chọn các User Story trên và chia thành các task nhỏ (sub-task).
o Daily Scrum (15 phút mỗi ngày): Họp nhanh để cập nhật tiến độ.
o Sprint Review (Ngày 21/11, buổi chiều): DEMO sản phẩm chạy được cho cả nhóm và "khách hàng".
o Sprint Retrospective (Ngày 21/11, cuối giờ): Nhìn lại quá trình làm việc để cải tiến cho Sprint 4.
Bảng công việc (Sprint Backlog) cho Sprint 3 trên Trello/Jira:
Công việc | Người phụ trách | Công việc cần làm (Sub-tasks) | Deadline | Kết quả/Deliverable
User Story 1: Thêm bài học/chương | Thành viên A | - Thiết kế bảng lessons | (12/11) | Giảng viên thêm/sửa/xóa bài học trong khóa học
- Viết API POST/PUT/DELETE /lessons
- Tạo giao diện thêm/sửa/xóa bài học
- Tích hợp API và UI
User Story 2: Upload tài liệu cho bài học | Thành viên B | - Thêm field tài liệu vào bảng lessons | (15/11) | Giảng viên upload tài liệu cho từng bài học
- Viết API upload file
- Tạo giao diện upload
- Tích hợp API và UI
User Story 3: Sinh viên xem bài học | Thành viên C | - Viết API GET /course/:id/lessons | (18/11) | Sinh viên xem nội dung các bài học đã ghi danh
- Tạo giao diện danh sách bài học
- Hiển thị nội dung bài học
- Viết test case
User Story 4: Tải tài liệu từ bài học | Thành viên D | - Tạo nút tải tài liệu | (21/11) | Sinh viên tải tài liệu từ bài học
- Viết API download file
- Tích hợp API và UI
- Kiểm thử chức năng tải file
Kiểm thử chéo & Sửa lỗi | Cả team | - Test chéo các chức năng | (21/11) | Sản phẩm ổn định, sẵn sàng cho Sprint Review
- Log bug và fix
- Tổng hợp để chuẩn bị Sprint Review
Sprint 4: Hoàn thiện tính năng nộp bài, chấm điểm và tối ưu (ngày 24/11 -> 5/12)
Sprint Goal: Hoàn thiện luồng học tập cơ bản với chức năng bài tập và chấm điểm. Tối ưu giao diện và sửa các lỗi còn tồn đọng để chuẩn bị cho buổi demo cuối cùng.
Các sự kiện Scrum:
o Sprint Planning (Ngày 24/11): Cả nhóm họp để chọn các User Story trên và chia thành các task nhỏ (sub-task).
o Daily Scrum (15 phút mỗi ngày): Họp nhanh để cập nhật tiến độ.
o Sprint Review (Ngày 5/12, buổi chiều): DEMO sản phẩm chạy được cho cả nhóm và "khách hàng".
o Sprint Retrospective (Ngày 5/12, cuối giờ): Nhìn lại quá trình làm việc để cải tiến cho Sprint 4.
Bảng công việc (Sprint Backlog) cho Sprint 4 trên Trello/Jira:
Công việc | Người phụ trách | Công việc cần làm (Sub-tasks) | Deadline | Kết quả/Deliverable
User Story 1: Tạo bài tập cho khóa học | Thành viên A | - Thiết kế bảng assignments | (24/11) | Giảng viên tạo bài tập, đặt hạn nộp
- Viết API POST /assignments
- Tạo giao diện tạo bài tập, đặt hạn nộp
- Tích hợp API và UI
User Story 2: Sinh viên nộp bài tập | Thành viên B | - Viết API upload bài tập | (27/11) | Sinh viên upload bài tập thành công
- Tạo giao diện upload file
- Tích hợp API và UI
- Viết test case upload
User Story 3: Giảng viên chấm điểm | Thành viên C | - Viết API chấm điểm | (02/12) | Giảng viên chấm điểm, nhận xét bài nộp
- Tạo giao diện chấm điểm, nhận xét
- Cập nhật điểm số vào DB
- Viết test case chấm điểm
User Story 4: Tối ưu UI/UX & fix bug | Thành viên D | - Thu thập feedback | (05/12) | Giao diện tối ưu, lỗi đã fix, sản phẩm hoàn thiện
- Tối ưu giao diện
- Sửa lỗi các sprint trước
- Viết test case regression
- Review code
Kiểm thử chéo & Chuẩn bị Demo cuối | Cả team | - Kiểm thử toàn bộ | (05/12) | Sản phẩm hoàn thiện, sẵn sàng demo
- Log bug và fix
- Chuẩn bị demo cuối cùng cho Sprint Review