## W7 (2109~)
PROJECT REPORT
Group | SEP490-SE_54
Week | 14/09/2026-20/09/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Build shared layout foundation for UI (Header, Footer, ...) | Minh Khôi | Completed
| Code and Specify use cases for Sprint 1: 01-Register, 02-Login, 03-Google Login, 04-Log Out | Hoàng | In Progress
| Code and Specify use cases for Sprint 1: 07-View Learner Profile, 08-Update Learner Profile | Minh Khôi | In Progress
| Code and Specify use cases for Sprint 1: 12-Purchase Credits (with real payment API integrated), 13-View Credit History | Mạnh | In Progress
| Code and Specify use cases for Sprint 1: 11-View Credit Packages, 14, 15, 16-Admin CRUD Credit Package | Gia Khôi | Completed
| Code and Specify use cases for Sprint 1: 05-Reset Password, 06-Change Password | Trường | In Progress
Pending
Pending
Pending
Pending
Pending
Pending
Pending
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W8 (2809~)
PROJECT REPORT
Group | SEP490-SE_54
Week | 14/09/2026-20/09/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Build shared layout foundation for UI (Header, Footer, ...) | Minh Khôi | Completed
| Code and Specify use cases for Sprint 1: 01-Register, 02-Login, 03-Google Login, 04-Log Out | Hoàng | In Progress
| Code and Specify use cases for Sprint 1: 07-View Learner Profile, 08-Update Learner Profile | Minh Khôi | In Progress
| Code and Specify use cases for Sprint 1: 12-Purchase Credits (with real payment API integrated), 13-View Credit History | Mạnh | In Progress
| Code and Specify use cases for Sprint 1: 11-View Credit Packages, 14, 15, 16-Admin CRUD Credit Package | Gia Khôi | Completed
| Code and Specify use cases for Sprint 1: 05-Reset Password, 06-Change Password | Trường | In Progress
Pending
Pending
Pending
Pending
Pending
Pending
Pending
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes